## ResealPrep
Button | Data
18F | Completed The work was completed before Chrismast
18D | Currently working on Only one fullwidth treatment location to be done. There was other two locations, but because the underlying layer is BTB, and removal of BTB will reduce the overall pavement strength so the method of treatment is BTB
24D | Completed The work was completed before Australian day. Work has been paid, the remaining to be claim isfor EOT1 and EOT value about 40k

## RMPC
18D | Asphalt Patching
State control road | Asphalt Patching only a few locations
Move to work on RMPC location on road 24D near the town

## Noondoo Project
Current status
Waiting for addition $200k
Waiting for the council to send through certificate of currency for their insurance