## Project Alpha
Task Name | Description | Status | Assigned To | Priority | Deadline | Issues/Notes
Design Phase | Complete UI mockups and design system | In Progress | John Smith | High | 2024-02-15 | Waiting on client feedback for color scheme
Backend API | Build REST endpoints for user management | Not Started | Sarah Chen | Medium | 2024-02-28 | Requires design completion first
Database Setup | Configure production database | Completed | Mike Johnson | High | 2024-02-01 | Done ahead of schedule
Frontend Development | Implement responsive UI components | In Progress | Emily Davis | High | 2024-03-05 | Need to finalize component library
Testing & QA | Conduct comprehensive testing | Not Started | Alex Wong | Medium | 2024-03-15 | Test environment setup pending
Testing & QA | Implement responsive UI components | In Progress | Alex Wong | Medium | 2024-03-15 | Test environment setup pending

## Project Beta
Task Name | Description | Status | Assigned To | Priority | Deadline | Issues/Notes
Requirements Gathering | Gather and document client requirements | In Progress | Jane Parker | High | 2024-02-10 | Meeting scheduled for Feb 8
Wireframes | Create initial wireframes and mockups | Not Started | Tom Wilson | Medium | 2024-02-20 | Waiting on requirements approval
Architecture Design | Design system architecture and data flow | Not Started | Sarah Chen | High | 2024-02-25 | Need to review scalability options
Security Audit | Conduct security vulnerability assessment | Not Started | Mike Johnson | High | 2024-03-10 | External consultant may be needed
Documentation | Write technical and user documentation | Not Started | Emily Davis | Low | 2024-03-20 | Template to be finalized

## Project Gamma
Task Name | Description | Status | Assigned To | Priority | Deadline | Issues/Notes
API Integration | Integrate third-party APIs | Completed | Alex Wong | High | 2024-01-30 | Successfully integrated all APIs
Payment Gateway | Setup payment processing system | In Progress | John Smith | High | 2024-02-18 | Stripe integration 80% complete
User Dashboard | Build comprehensive user dashboard | Not Started | Tom Wilson | Medium | 2024-03-01 | Awaiting design approval
Mobile Optimization | Optimize site for mobile devices | Not Started | Jane Parker | Medium | 2024-03-08 | Performance testing required

## Noondoo Project
Task Name | Description | Start Chainage | End Chainage | Side | Status
Clearing and Grubbing | CL-213-033 | 1 | 2 | LHS | Working on